## Actividades realizadas
Date | ¿Who? | Dificulty | Project | Task | ¿How much time it takes? | How I felt doing this task? Why? | What I learned?
2019-02-20 | Edwin | Easy | HCI general work | Make the bitácora | 2 mins. | Nice, that was easy :9
2019-02-26 | Mauricio | Medium | App Definition | Goals | 12 mins (11:11 - 11:23) | Fine, the goal was previously sketched
|  |  |  | Users | 18 mins (11:32 - 11:50) | Nice, the definition of possible users was an interesting task.
|  |  |  | Similar Systems | 21 mins (12:02 - 12:23) | Ok, the research was made before so it was a pretty boring task
2019-02-25 | Edwin | Medium | App requests | Interview | 2 hours (05:30 - 07:00) | Nice, I made a small talk with different Stakeholders
2019-02-26 | Edwin | Medium | App requests | Requeriments | 1.5 hours (03:30 - 05:00) | Ok, I made progress in the requirements
2019-02-26 | Edwin | Easy | First delivery | Reviews | 15 mins (05:00 - 05:15) | Nice, but I have some anotations
2019-02-26 | Kirbey | Medium | Elementos de innovavion, relevanvia y motivación | Define each point | 1 hr 37 min (20:40-22:17) | I fell a little tired, because I need to think all our pointview about each theme
2019-02-27 | Kirbey | Medium | Calendarización | Make the scheduling of project activities | 28 min (7:41-8:09) | Nice, it was only organizate the tasks
2019-02-27 | Edwin | Easy | First delivery | Presentation | 30 mins (8:00 - 8:30) | Nice, too easy, we had all the info | Having the information is easier to make a presentation and takes less time

## Actividades definidas
1.- Definición de la aplicación | Mauricio
2.- Plan de investigación | Jorge
3.- Calendario de actividades | Kirbey
4.- Perfiles, personas, escenarios | Mauricio/Kirbey
5.- Definición de requerimientos | Edwin/Jorge
6.- Presentación | Edwin
7.- Revisiónes | Edwin

## Metricas
Medicion de tiempos resultares semanales.
Dificulty | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Easy | 1 hour
Medium | 2 hours
Hard | 3 hours
Promedio de estado de ánimo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio
Contribuciónes del equipo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio
Velocidad del equipo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio