## Actividades realizadas
Date | ¿Who? | Dificulty | Project | Task | ¿How much time it takes? | How I felt doing this task? Why? | What I learned?
2019-02-20 | Edwin | Easy | HCI general work | Make the bitácora | 2 mins. | Nice, that was easy :9
2019-02-26 | Mauricio | Medium | App Definition | Goals | 12 mins (11:11 - 11:23) | Fine, the goal was previously sketched
|  |  |  | Users | 18 mins (11:32 - 11:50) | Nice, the definition of possible users was an interesting task.
|  |  |  | Similar Systems | 21 mins (12:02 - 12:23) | Ok, the research was made before so it was a pretty boring task
2019-02-25 | Edwin | Medium | App requests | Interview | 2 hours (05:30 - 07:00) | Nice, I made a small talk with different Stakeholders
2019-02-26 | Edwin | Medium | App requests | Requeriments | 1.5 hours (03:30 - 05:00) | Ok, I made progress in the requirements
2019-02-26 | Jorge | Medium | First delivery | Plan de investigación | 2 hours (12:30 - 2:30) | Ok, I had doubts of how I should do it
2019-02-26 | Edwin | Easy | First delivery | Reviews | 15 mins (05:00 - 05:15) | Nice, but I have some anotations
2019-02-26 | Kirbey | Medium | Elementos de innovavion, relevanvia y motivación | Define each point | 1 hr 37 min (20:40-22:17) | I fell a little tired, because I need to think all our pointview about each theme
2019-02-27 | Kirbey | Medium | Calendarización | Make the scheduling of project activities | 28 min (7:41-8:09) | Nice, it was only organizate the tasks
2019-02-27 | Edwin | Easy | First delivery | Presentation | 30 mins (8:00 - 8:30) | Nice, too easy, we had all the info | Having the information is easier to make a presentation and takes less time
2019-03-05 | Jorge | Medium | App requests | Interview | 2 hours (18:00 - 20:00) | Ok, the perspective's interviewed was interesting and gave ideas about the future the app
2019-02-16 | Mauricio | Medium | App requests | RoundTable | 1hr 30 min (19:00 - 20:30) | Great, it was interesting to gather new points of view and the activity was enjoyable. | Some other reasons that causes people to feel depressed.
2019-02-17 |  | Medium | App requests | RoundTable Report | 45 min (12:59 - 13:44) | Nice, even tough the justification of the technique was a bit boring, remembering the activity was nice.
|  | Medium | App requests | Making the inspection methods document | 2hr 45 min (23:03-01:48) | I fell a little confused, cause I dont understand at the begining what I need to do correctly, so i need to correct my work 2 times

## Actividades definidas
Task | Person | Difficulty
1.- Definición de la aplicación | Mauricio | Medium
2.- Plan de investigación | Jorge | Medium
3.- Calendario de actividades | Kirbey | Easy
4.- Perfiles, personas, escenarios | Mauricio/Kirbey | Hard
5.- Definición de requerimientos | Edwin/Jorge | Hard
6.- Presentación | Edwin | Easy
7.- Revisiónes | Edwin | Easy

## Metricas
Medicion de tiempos resultares semanales.
Dificulty | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Easy | 1 hour
Medium | 2 hours
Hard | 3 hours
Promedio de estado de ánimo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio
Contribuciónes del equipo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio
Velocidad del equipo
Person | Week 0 | Week 1 | Week 2 | Week 3 | Week 4
Edwin
Kirbey
Jorge
Mauricio